## Timeline Summary
Treasury Market Updates - Development Timeline
# | Work item | What it covers | Mandays
1 | Foundation & setup | Project scaffold, login, user accounts, database | 2
2 | Daily data-collection engine | System that pulls, checks and stores the rates every evening, with retries and error logging | 2.5
3 | Connecting the market data sources | BSP rates, FX summary, BVAL, PSE stocks, inflation & GDP, oil, and the paid vendor for gold / wheat / LME lead | 17
4 | Building the dashboard screens | Card layout from the screenshots, sections / tabs, value + change indicators, all charts, click-through detail view | 6.5
5 | Admin & monitoring tools | Manage sources, re-run a pull, override a value, set alert thresholds | 5.5
6 | Testing & reliability | Automated tests and hardening so daily pulls don't silently break | 4.5
7 | Planning, sign-off, docs & user testing | Requirements, design approval, runbook, UAT with Treasury and Jonar | 5
| Subtotal |  | 43
| Buffer (~15%) |  | 7
| TOTAL |  | 50